## Template - Deliverables and Cos
Officer's cost per man day
List of Activities and Deliverables
Phase | Milestones | Activity | Deliverables | Working days | Estimated cost | Timeframe | Subtotals (per Milesone)
1 | Building a Food Waste (FW) Task Force | Property Kick-off | - Consultant to assist with establishing an internal FW Task Force and announcing initiative to staff and department leaders - Consultant to hold a 2 hours face-to-face kick off meeting with task force members - Consultant to provide detailed work plan and timeline to task force | 2 | 0 | The course of 2 weeks
|  | Staff Engagement | - Consultant to provide (online) survey on staff's perception of FW situation at the property and knowledge on the global issue of food loss and waste (pre-project) - Consultant to hold workshop/learning session for all staff to raise awareness about the environmental impact of food loss and waste | 2 | 0
|  | General Consultation and Reporting | - Consultant to send out weekly emails to task force members with updates and next steps - Consultant to gather reported data, feedback and survey results - Consultant to track initiative progress | 1 | 0 |  | 0
2 | Setting a Data Baseline | Adopting a Separation and Measurement System | - Consultant to advise task force on choosing type of FW separation and measurement system and assist with bin placement | 1 | 0 | The course of 5 weeks
|  | Staff Training | - Consultant to assist with building awareness, providing knowledge and skills required to adjust to the new separation scheme | 1 | 0
|  | Gathering Baseline Data and Setting a Goal | - Consultant to assist with ensuring accurate data collection from FW measurement to plot trends and establish baseline - Consultant to assist with follow up trainings for staff to reinforce new separation scheme and accurate measurement - Consultant to advise task force on setting measurable FW reduction goal and engaging staff to work towards achieving it | 2 | 0
|  | General Consultation and Reporting | - Consultant to send out weekly emails to task force members with updates and next steps - Consultant to gather reported data and feedback - Consultant to track initiative progress | 2 | 0 |  | 0
3 | Adopting interventions | Prevention - Reduced Waste Menu Design | - Consultant to provide guidance for experimenting with reduced waste menu design | 1 | 0 | The course of 8 weeks
|  | Prevention - Reduced Waste Buffet Design | - Consultant to provide resources to experiment with reduced waste buffet design | 1 | 0
|  | Prevention - Guest-facing Messages | - Consultant to provide resources to experiment with guest-facing messages | 1 | 0
|  | Prevention - Reduced Waste Events | - Consultant to assist task force with coordinating actions to take for reduced waste events | 1 | 0
|  | Prevention - Employee Empowerment | - Consultant to provide resources to engage staff and run staff activities | 1 | 0
|  | Prevention - FW Audit | - Consultant to organise and perform FW audit with Executive Chef and Culinary team to determine key drivers of FW | 1 | 0
|  | Donation | - Consultant to assist with exploring feasible food donation opportunities and ensuring appropriate tracking and reporting of donation initiatives - Consultant to assist with training staff on new processes (if needed) | 1 | 0
|  | Diversion | - Consultant to assist with exploring and evaluating feasible solutions to divert organic waste from landfill and conventional hauling - Consultant to provide updates (if any) on relevant policies or regulations on waste disposal requirements - Consultant to assist with training staff on new processes (if needed) | 1 | 0
|  | General Consultation and Reporting | - Consultant to send out weekly emails to task force members with updates and next steps - Consultant to provide necessary resources to help track and report back data and feedback for all intervention phases - Consultant to compile and analyse reported data and feedback results to access progress against goals - Consultant to assist task force with understanding continued problem areas and establishing new goals | 2 | 0 |  | 0
4 | Institutionalising change | Initiative Review and Staff Engagement | - Consultant to meet with FW task force members to review the outcomes of the initiative, including successes, challenges and next steps - Consultant to assist with establishing new goals and determining additional opportunities for FW reduction and management covering all food outlets - Consultant to provide (online) survey on staff's perception of FW situation at the property and knowledge on the global issue of food loss and waste (post-project) and to compare survey outcomes (pre- and post-project) - Consultant to assist with communicating initiative outcomes to staff and celebrating success | 1 | 0 | The course of 1 week
|  | General Consultation and Reporting | - Consultant to send out weekly email to task force members with updates and next steps - Consultant to gather data and feedback to compile a project report highlighting key achievements and outcomes following the initiative | 1 | 0 |  | 0
|  |  | Total: | 23 | 0 | 16 weeks
Note on E9: Pete's comment: This should include recommendations to use technology 'like' the Winnow platform. -Veronika Forstmeier

## Template - Timeline
[Consultant]/[Hotel property]
Hotel Kitchen Program – Overall Workplan & Timeline
| Phase 1 - Building your task force (3 weeks) | Responsible […] Lead | Deliverables | Status | Due Date | Actual Date | [Month], [Year] |  |  |  | [Month], [Year] |  |  |  | [Month], [Year] |  |  |  | [Month], [Year] |  |  |  | [Month], [Year] |  |  |  | [Month], [Year]
| Tasks | [5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
a. | Share news of the food waste initiative with property department leaders and staff |  | Announce initiative to staff and department leaders | bar: [Month], [Year] W1
b. | Send the first weekly email to department leads |  | Recruit Task Force Members and send first weekly update on project status and next steps via Email | bar: [Month], [Year] W1
c. | In-person launch meeting for the task force |  | Schedule the first meeting of the task force and hold a 2 hours in-person meeting | bar: [Month], [Year] W1
d. | Assess need for new bins to collect food waste |  | Procure/allocate bins and scales | bar: [Month], [Year] W2
| Building awareness among all staff |  | Train/educate all staff on environmental impact of food waste | bar: [Month], [Year] W2
e. | Staff survey |  | Conduct staff survey (pre-project) on their perception of food waste situation at the property and knowledge on the global issue of food loss and waste | bar: [Month], [Year] W2
f.
| Phase 2 - Setting a data baseline (4 weeks) | Responsible […] Lead | Deliverables | Status | Due Date | Actual Date | [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]
| Tasks | [5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
a. | Convene task force |  | Schedule task force meeting to discuss activities and deliverables of Phase 2 | bar: [Month], [Year] W3
b. | Train all relevant staff |  | Build awareness, provide knowledge and skills required to adjust to the new separation scheme | bar: [Month], [Year] W3 to [Month], [Year] W4
c. | Separate and measure |  | Coordinate and ensure accurate separation and measurement with relevant staff and reinforce new practice through onsite visits/check-ins if required | bar: [Month], [Year] W4 to [Month], [Year] W3
d. | Track measured food waste data |  | Measure food waste to plot trends and understand impacts of food waste | bar: [Month], [Year] W3 to [Month], [Year] W3
e. | Send weekly emails |  | Send weekly updates on project status and next steps via Email | bar: [Month], [Year] W3 to [Month], [Year] W3
f.
| Phase 3- Intervention Implementation (8 weeks) | Responsible […] Lead | Deliverables | Status | Due Date | Actual Date | [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]; [Month], [Year] W1: [Month], [Year]
| Tasks | [5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
a. | Convene task force |  | Schedule task force meeting to discuss activities and deliverables of Phase 3 | bar: W4
b. | Adopt Interventions - Experiment with reduced waste menu design |  | Train relevant staff using Lobster Ink videos. Work with department leaders to reinforce or disseminate training messages. | bar: W1
c. | Adopt Interventions - Experiment with reduced waste buffet design |  | Provide resources to experiement with reduced waste buffet design | bar: W2
d. | Adopt Interventions - Experiment with guest-facing messages |  | Provide resources to experiment with guest-facing messages | bar: W2
e. | Adopt Interventions - Coordinate culinary, banquet and sales departments for reduced waste events. |  | Host meeting with relevant departments to coordinate actions to take for reduced waste events | bar: W3
f. | Adopt Interventions - Employee empowerment/competition |  | Provide resources to engage staff and run staff activities Support the coordination of a Clean Plate Challenge Photo Contest if feasible | bar: W4
g. | Adopt Interventions - Food waste audit |  | Organise and perform food waste audit with Executive Chef and Culinary teamPerform an event audit to determine key drivers of food waste | bar: W1
h. | Adopt Interventions - Donation |  | Explore and evaluate feasible food donation opportunities | bar: W2
i. | Adopt Interventions - Diversion |  | Explore and evaluate feasible solutions to divert organic waste from landfill and conventional hauling | bar: W3
j. | Track data |  | Provide necessary resources to help track and report back data | bar: W1 to W3
k. | Collect feedback |  | Encourage staff to report back any feedback on adopted interventions and the project (progress) in general Collect and compile feedback to task force members | bar: W3
l. | Send weekly emails |  | Send weekly updates on project status and next steps via Email | bar: W1 to W3
| Phase 4 - Institusionalising change (1 week) | Responsible […] Lead | Deliverables | Status | Due Date | Actual Date | W1: [Month], [Year]; W1: [Month], [Year]; W1: [Month], [Year]; W1: [Month], [Year]; W1: [Month], [Year]; W1: [Month], [Year]
| Tasks | [5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
a. | Staff survey |  | Conduct staff survey (post-project) on their perception of food waste situation at the property and knowledge on the global issue of food loss and waste Compare survey outcomes (pre- and post-project) | bar: W4
b. | Convene task force |  | Host meeting with task force members to review the outcomes of the initiative Review the percentage or total change in food waste following interventions Review successes, challenges and next steps | bar: W4
c. | Communicate initiative outcomes to staff & celebrate success |  | Communicate initiative outcomes to staff and set goals to institutionalise effective behaviors in functional teams | bar: W4
d. | Develop workplan to roll out food waste reduction efforts in all food outlets |  | Access progress against goals, understanding continued problem areas, establishing new goals and determining additional opportunities for food waste reduction and management | bar: W4
e.
| Post-Project | Responsible WWF Lead | Work to be undertaken/Deliverables | Status | Due Date | Actual Date | W1: [Month], [Year]; W1: [Month], [Year]; W1: [Month], [Year]; W1: [Month], [Year]; W1: [Month], [Year]; W1: [Month], [Year]
| Tasks | [5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
a. | Analyse data and feedback |  | Gather and analyse data and feedback including overall satisfaction of task force members | bar: [Month], [Year] W1 to [Month], [Year] W2
b. | Compile project report |  | Provide project report to task force members | bar: [Month], [Year] W3 to [Month], [Year] W4
c. | Create case study |  | Create case study to be shared publicly (optional) showcasing successes of the initiative | bar: [Month], [Year] W3 to [Month], [Year] W4
d.